## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
MP01 | Balance System | As a user, I want to check my balance , so that I can know whether my balance can pay for my course and whether I need to recharge. | Very High | Iteration 1 | 1.My account balance will be shown directly on the home page. 2.The home bar has a button to enter the interface of recharge. | MP - 'Me' Page | 2021-03-29 | 2021-04-09
MP02 | Membership Level | As a user, I want to check my Menbership level so that I check what services and rights are available under the corresponding membership level | Medium | Iteration 2 | 1.The home bar shows my Membership level directly. 2.I can view the privileges and services I have and as well as those of other levels' by clicking on "Membership Details". | MP - 'Me' Page | 2021-04-12 | 2021-04-23
MP03 | Marked Video | As a user, I want to check my marked video so that I can go straight to the videos I've been marked. | Low | Iteration 3 | 1. User can watch the videos directly on the "Marked video" interface. 2.Support editing of marked videos. | MP - 'Me' Page | 2021-04-26 | 2021-05-07
MP04 | Personal Information | As a user, I want a personal home page,so that I can modify my personal information after regist in and customize my home page. | Low | Iteration 3 | 1.I can go to my personal information section to modify my personal information at any time. 2.All information except the user ID originally generated should be modifiable. | MP - 'Me' Page | 2021-04-26 | 2021-05-07
MP05 | FAQ & Contact Customer Service | As a user, I want to contact coustomer service, so that I can ask for solutions to any questions I have when using the software. | Medium | Iteration 2 | 1.Basic questions are listed in the form of questions with answers.For other questions provide human customer service phone number. 2.Basic questions include but not limited to how to recharge, how to upgrade the membership level, software use tutorials, etc. 3.Other questions include but not limited to recharge failure, video playback problems, etc. 4.Click the customer service button on my page to view all customer service. | MP - 'Me' Page | 2021-04-12 | 2021-04-23
MP06 | View Payment Records | As a user, I want to see all my payments records, so that I can see my total spending. | Very Low | Iteration 4 | 1.All payments records are are sorted and displayed according to the time of the payment time. | MP - 'Me' Page | 2021-05-10 | 2021-05-21
LS01 | Check Available Live Sessions' Time-slots | As a user, I want to check the time-slots of each coach so that I can arrange training time according to my own time. | Very High | Iteration 1 | 1. Make sure that the free time of each coach can be displayed and browsed. 2. Make sure that the free coaches can be found according to a certain time period. 3. Make sure that the coach can be search by names. 4. Verify that the contents and theme can be searched. | LS - Live Session | 2021-03-29 | 2021-04-09
LS02 | Check the Details and Contents of Live Seesions | As a user, I want to view the available content and detailed information of each coach so that I can choose properly. | High | Iteration 2 | 1. Make sure that it can display the personal information of each coach. 2. Make sure that the details can be displayed correctly and correspondingly. | LS - Live Session | 2021-04-12 | 2021-04-23
LS03 | Rank the Coaches | As a user, I want to rank the coach afterwards so that I can evaluate each coach I had. | Very Low | Iteration 4 | 1. Make sure that my rank has been recorded. 2. Make sure that the average ranks of the coach can be displayed. | LS - Live Session | 2021-05-10 | 2021-05-21
LS04 | Book A Live Session | As a user, I want to book a particular live session so that I can enjoy my membership privilege. | Very High | Iteration 1 | 1. Verify that while booking, the corresponding details can be displayed. 2. Verify that the corresponding info will be recorded into the files. | LS - Live Session | 2021-03-29 | 2021-04-09
LS05 | A Recommendation System for Live Session | As a user, I want to let the system automatically recommend some coaches for me. | Low | Iteration 3 | 1. Verify that only a coach who is available can be recommended. 2. Verify that only a coach who has more than 8.0/10.0 rating can be recommended. 3. Verify that the recommendation can be dispalyed on the Live Session page. | LS - Live Session | 2021-04-26 | 2021-05-07
LS06 | Coaches' Performance | As a user, I want to see the coach’s class records so that I can judge the coach’s teaching effectiveness. | Medium | Iteration 2 | 1. Make sure that the coach’s class records are recorded. 2. Make sure that the corresponding members can be found according to the coach’s class records. | LS - Live Session | 2021-04-12 | 2021-04-23
VW01 | Search Videos by Keyword | As a user, I want to find relevant videos by entering keywords in the video watching interface, so that I can find the specific video. | Medium | Iteration 2 | 1.When the keywords entered by the user cannot match any video,search results should show that the video does not exist. 2.There is a return button to stop searching and return the user to the previous page at any time. 3.The search function is realized through the search box at the top of the video watching page. 4.When the user enters keywords and clicks the search button,the search begins and the relevant video should be displayed below the search box. | VW - Video Watching | 2021-04-12 | 2021-04-23
VW02 | Browse Videos by Categories | As a user, I want to filter different categories of videos by selecting different categories in the video watching interface, so that I can choose my favorite type. | High | Iteration 1 | 1.The categories of videos should include but not limited to yoga, HIIT, strength, aerobic, anaerobic etc. 2.The selection of categories can support single selection and multiple selection. 3.All videos should be read from the file that holds all videos. | VW - Video Watching | 2021-03-29 | 2021-04-09
VW03 | Browse All the Videos | As a user, I want to browse all the videos in the video watching interface, so that I can choose a video. | Very High | Iteration 1 | 1.When the number of videos is large, the number of videos displayed on a page should be limited and the user can browse all the videos through turning the pages. 2.Users should be able to jump to the corresponding page by entering the page number. | VW - Video Watching | 2021-03-29 | 2021-04-09
VW04 | View Watching History | As a user, I want to view the watching records, so that I can simply playback. | Very Low | Iteration 4 | 1.The user's watching records are sorted and displayed according to the time in which the video was played. 2.Videos viewed by the user are stored in a file from which the recrods should be read. | VW - Video Watching | 2021-05-10 | 2021-05-21
VW05 | Add as Fafourite | As a user, I want to mark the videos, so that I can view them directly next time. | Low | Iteration 3 | 1. Make sure that you can mark any place of the videos. 2. Make sure that user can find the previously marked video sign when re-enter the system. | VW - Video Watching | 2021-04-26 | 2021-05-07
VW06 | A Recommendation System for Video Watching | As a user, I want to let the system automatically recommend some courses for me. | Low | Iteration 3 | 1. Verify that the recommendation can be dispalyed on the Live Session page. | VW - Video Watching | 2021-04-26 | 2021-05-07
MBS01 | Purchase Hierachical Membership | As a user, I want to purchase a hierachical membership so that i can enjoy different services. | Very High | Iteration 1 | 1.Make sure you offer the option for different members to buy when you buy a membership. 2.Purchasing members can make purchases on their personal pages. 3.When the member purchase is successful, the member status will be updated in the personal information file in time. 4. After successful purchasing, the correspoing data should be recorded into files. | MBS - Membership | 2021-03-29 | 2021-04-09
MBS02 | Top-up | As a user I want to top-up my account so that I can buy class. | Very High | Iteration 1 | 1.In the personal information interface there is a "My Account" button, I can recharge the balance. 2. Users can customize the amount of recharge. 3. Verify that all of the successful operations are recorded into files. 4. If my balance is not enough to pay for the product, a pop-up will remind me to top-up. | MBS - Membership | 2021-03-29 | 2021-04-09
MBS03 | Discount | As a user, I want to purchase a membership so that I can enjoy discounts for other services | Low | Iteration 3 | 1.Make sure the benefits changes applied after you purchase the membership. 2. Verify that there are many options available when purchasing membership, and the privileges of these different members vary. 3. When users don't possess a certain privilege, the message of purchasing a higher-membership will display for recommending. | MBS - Membership | 2021-04-26 | 2021-05-07
MBS04 | Regular member | As a user, I want use basic function as a regular member so that i can save money. | Very High | Iteration 1 | 1.In some functions, such as booking coaches, members are checked to see if the level is sufficient. 2.Membership limits are not set for lower-level functions such as viewing videos. 3.For each level of membership, ensure that their rights do not conflict. | MBS - Membership | 2021-03-29 | 2021-04-09
MBS05 | Membership Statistical Information | As a user, I want to view the membership information, so that I can adjust business practices. | Very Low | Iteration 4 | 1. Verify that the information of members, including the number of members and etc are displayed on the Membership page. | MBS - Membership | 2021-05-10 | 2021-05-21
MBS06 | See Other Members' Coach | As a user, I want view the training records of excellent members so as to help me find excellent coaches. | Very Low | Iteration 4 | 1. Make sure that the members’s class records are recorded. 2. Make sure that the corresponding coaches can be found according to the members’ class records. | MBS - Membership | 2021-05-10 | 2021-05-21
MBS07 | Upgrade Member | As a user, I want to upgrade my membership so that have a better experience. | High | Iteration 1 | 1. The member status in the profile file will be updated after successful operation. 2. The member status in the personal files of the member will be updated. | MBS - Membership | 2021-03-29 | 2021-04-09
OTS01 | Convenient Button | As a UI desiginer I want every layer of the UI is clear enough for users to opreat(e.g. distinct exit/go-back button) so that I can give the user a better experience | Very High | Iteration 1 | 1.Check all the pages to make sure each page has a return button. 2.Make sure the user remains available before logging out. | OTS - Others | 2021-03-29 | 2021-04-09
OTS02 | Fault Tolerance | As a product manager I want the product has some fault tolerance so that it won't break down easily. | Medium | Iteration 2 | 1. Make sure that each error is handled after it is thrown. 2. Make sure that some inputs entered by user should be examined if the format is correct. | OTS - Others | 2021-04-12 | 2021-04-23
OTS03 | Make Plans | As a user I want to make plans on the app so that record my workouts | Very Low | Iteration 4 | 1.Users can record their exercise data for the day. 2.Users can view their exercise data Each time the user records the movement information, in the file update. | OTS - Others | 2021-05-10 | 2021-05-21
OTS04 | Payment | As a customer, I want to know the amount of consumption intuitively, and choose my own payment method, cash or card, so that I can pay the bill with preferable method of payment except using the virtual stamps. | High | Iteration 1 | 1. The system can list all the order choices and consumption amounts for customers to confirm. 2. Customers can directly see the entrance of two payment methods, cash or bank card. | OTS - Others | 2021-03-29 | 2021-04-09
OTS05 | Register | As a customer, I want to register as a member, so that I can get a discount when the condition is met. | Very Low | Iteration 4 | 1. Customers must enter their fistname and surnaem, as well as at least one between email and mobile number to register. 2. When the format of the user's email or mobile numver is incorrect, a popup dialog is shown to remind him/her and it cannot be registered. 3. Upon registering successfully, customers can receive an email or SMS with 8-digit membership number. | OTS - Others | 2021-05-10 | 2021-05-21
OTS06 | Bill | As a customer, I want to get a bill with relevant information after each purchase, so that I can keep vouchers for every purchase. | Medium | Iteration 2 | 1. Regardless of whether the user uses cash, bank card or virtual stamp to pay, the system will provide a related ticket(i.e. a txt file). 2. The bill should have the order number, the name of user, the amount of consumption, and other necessary relevant information. | OTS - Others | 2021-04-12 | 2021-04-23
OTS07 | Login | As a manager, I want to restrict the access of non-membership users so that can preserve the copyrights. | Very Low | Iteration 4 | 1. After login successfully, all non-membership user will be disaplayed Membership page, noting that if want to countinue browsing the contents, they need to purchasing the correspoing memberships. | OTS - Others | 2021-05-10 | 2021-05-21
S4C01 | Check the Class Schedule by Week | As a personal trainer, I want to check the class schedule by week, so that I can check my work time and balance work and life. | High | Iteration 1 | 1.Read all the courses of a week and the information related to the courses, including the date, time and name of each course from the sechedule file. 2.The course schedule is displayed in the form of table, the horizontal axis is the date, the vertical axis is the time period, and the course name is displayed in the corresponding cell. 3.The class schedule of the week of the day is displayed by default 4.The search box is above the schedule. 5.The name of the course is a combination of the nickname of the student and the number of sessions. | S4C - System for Coaches | 2021-03-29 | 2021-04-09
S4C02 | Check the Class schedule by a Specific Date | As a personal trainer, I want to check the class schedule by the date entered, so thatI can look at my schedule for a particular day. | Very High | Iteration 1 | 1.Reads all courses and other information related to the courses, including the time and the name of each course, from the schedule file by the date entered. 2.The course schedule is displayed in the form of a single column table. The horizontal axis is the input date, the vertical axis is the time period, and the course name is displayed in the corresponding cell. 3.The search box is above the course schedule. Enter the date in the search box to query the corresponding date schedule. 4.The name of the course is a combination of the nickname of the student and the number of sessions. | S4C - System for Coaches | 2021-03-29 | 2021-04-09
S4C03 | Check the Course Progress by the Names of Students | As a personal trainer, I want to check the course progress by the nicknames of students, so that I I can view the current progress of each student's course. | Low | Iteration 3 | 1.Reads all courses and other information related to the courses, including the date, time and name of each course, from the schedule file by the nickname entered. 2.The schedule is displayed in a table, which includes two columns, date and time of each course respectively. Each row of the table shows the number of courses. 3.All the courses read from the file are displayed in the table according to the number of courses from small to large. 4.The search box is above the course schedule. Enter the nickname of student in the search box to query the corresponding courses. | S4C - System for Coaches | 2021-04-26 | 2021-05-07
S4C04 | Modify course information | As a personal trainer, I want to make a change about the course schedule so that make it easier to negotiate the course schedule with students | High | Iteration 1 | 1.The coach can add or delete the course time, and the change will be displayed at the student side. 2.The instructor can modify the scheduled course time and the change will be displayed on the student side. 3.When the course time conflicts, the teacher can not modify or add lessons | S4C - System for Coaches | 2021-03-29 | 2021-04-09
S4C05 | Check Rating by Course | As a coach, I want to check the ratings given to my courses by members so that I can measure the effectiveness of teaching. | Medium | Iteration 2 | 1. Make sure that the coach's class records can be found. 2. Ensure that the scores given to the coach by members are recorded. | S4C - System for Coaches | 2021-04-12 | 2021-04-23
S4C06 | Check Students' Rating | As a user, I want to check the grades given to me by a certain member, so that I can adjust the training standards for that member in time to better achieve the teaching purpose. | Medium | Iteration 2 | 1. Make sure that the scores given to the coach by the members are recorded. 2. Ensure that the scores given to coaches by members in each class can be recorded separately and can be queried. | S4C - System for Coaches | 2021-04-12 | 2021-04-23
S4C07 | Bonus Mechanism | As a coach, i want to have a commission/bonus mechanism so that promote the initiative of working. | Very Low | Iteration 4 | 1.Make sure every coach's session is recorded. 2.The amount of the commission is related to the length of the class and the personal evaluation after the class. 3.The coach's personal commission will be recorded in the coach information file. | S4C - System for Coaches | 2021-05-10 | 2021-05-21
S4C08 | Class Rearragement | As a coach, I want to transfer classes to other coaches when I have a time off work so that ensure the smooth running of the course. | Very Low | Iteration 4 | 1.Make sure you have the ability to transfer courses in the instructor's individual course view screen. 2.After the transfer of the course, the instructor's course schedule will be cancelled and the transferred instructor's course schedule will be updated in the course schedule file. | S4C - System for Coaches | 2021-05-10 | 2021-05-21
S4C09 | Coach home page | As a personal trainer, I want to have a home page to show my personal information, So that it will let the user have a more intuitive understanding of me | High | Iteration 1 | 1.The home page is divided into three sections:Basic information, class schedule, most popular courses. 2.Basic information should be provided: name, gender, grade point average, and type of course. 3.The schedule allows you to browse through all the course times of the week, and has different presentations for booked and unbooked courses. 4.The Subscribe button should be provided to the User on the Coach home page | S4C - System for Coaches | 2021-03-29 | 2021-04-09